## GANTT
GANTT Chart - Activity Name (Activity Code)
|  |  |  | Year 1 | [11 empty] | Year 2
WP | Leader |  | Name of the WP/Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
WP1 | Abc LTE | WP1 | Project Management and coordination | bar: Year 1 1 to Year 1 12
1 | Abc LTE | Task 1.1 | Planning and risk | bar: Year 1 1 to Year 1 12
1 | XYZ Srl | Task 1.2 | Data management | bar: Year 1 1 to Year 1 12
WP2 | JIO sl | WP2 | Solution Development | bar: Year 1 1 to Year 1 7
2 | XZY Srl | Task 2.1 | Requirement collection | bar: Year 1 1 to Year 1 2
2 | JIO sl | Task 2.2 | Lab test and finalization of the solution | bar: Year 1 2 to Year 1 7
WP3 | JIO sl | WP3 | Testing | bar: Year 1 7 to Year 1 9
3 | XZY Srl | Task 3.1 | Test at end-user premises | bar: Year 1 7 to Year 1 9
WP4 | Abc LTE | WP4 | Commercialization of the solution | bar: Year 1 3 to Year 1 12
4 | XZY Srl | Task 4.1 | Commercialization plan | bar: Year 1 3 to Year 1 6
4 | JIO sl | Task 4.2 | Product preview workshop with prospect partner | bar: Year 1 6 to Year 1 7
4 | Abc LTE | Task 4.3 | Testing with prospect partner and collection of EOIs and pre-orders | bar: Year 1 6 to Year 1 12
\
Based on the duration of your project, please provide the list of WPs, LEADERs, TASKs and TIME SPAN . In addition, indicate the end of the development phase and of the testing phase.
The names, descriptions and colours entered above are for information purpose only. Please remove this box.